## Cover sheet
Kosice ASU
Linde Project No. |  |  |  |  | Client Project No.
P1521051
Linde Project Code |  |  |  |  | Client Code
Kosice ASU
Linde Document Name |  |  |  |  | Client Doc. No.
Preliminary Constuction Schedule
Linde Doc. No. |  |  |  |  | Client Rev.
&AZ W-TT 1001(EN)
Preliminary Construction Schedule
Space for additional information - Enter if applicable or delete lines:
LE Entity |  |  |  | Sub-Project No. |  | Project Code
| Draft | 0.1 | 30.04.2024 | D. Puerta (GCE) |  |  | Draft
Gate | Status | Issue | Date | Prepared | Reviewed | Approved | Remark
© Linde The reproduction, distribution and utilization of this document as well as the communication of its contents to others without express authorization are prohibited. Offenders will be held liable for the payment of damages. All rights reserved in the event of the grant of a patent, utility model or design.
Form: &AZ-Q-PP 2020.610.01A (EN) / Issue 04 dated 01.10.2021
Draft

## Construction Schedule
Linde Project No. | [19 empty] | Linde Document Name | [17 empty] | Issue
P1521-051 | [19 empty] | Construction Schedule | [17 empty] | 0.1
Linde Project Code | [19 empty] | Linde Doc. No. | [17 empty] | Date
Kosice ASU | [37 empty] | 30.04.2024
| Year |  |  |  |  | 2 | 0 | 2 | 4 | [8 empty] | 2 | 0 | 2 | 5 | [8 empty] | 2 | 0 | 2 | 6 | [8 empty] | 2 | 0 | 2 | 7 | [8 empty] | 2 | 0 | 2 | 7
| Month | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Construction Permit Available
Constuction Works (Overall)
Equipment Delivery
Piping Delivery
Civil Works
Civil main foundation
Foundation of FBT Tanks
CB Foundation
Compressors (MAC) Foundations
Machine House Ring Beam
Machine House Floor
Molsieve Foundation
Civil small work
Roads / Paving / Landscaping
Under Ground Works
Cooling Water Line
Other Lines (Fire Fighting, Industrial SW…)
Structural Steel
Machine House Installation
Machine House Cladding
Overhead Crane Installation
Sleepers Structural Steel
Field Columns
Mechanical Equipment Installation
Main Air Compressors Inst./Erection
Motors
Electrical Substation
Molsieve Adsorbers
Vacuum Tanks
Pumps
Cold Boxes Erection
Cold Box Structural Steel Erection (and welding)
Columns Installation
Piping Installation inside box (by others)
Cold Box Lift
Heat Exchanger Lift
Connection Ducts Installation and Welding
Piping Works
Piping Prefabrication
Piping Field Installation
Pressure Testing and Re-instament
Painting
Insulation
Electrical & Instrumentation Works
Cable Trays Installation
Cable Pulling
Cable termination, testing and loop checks
Pre-Commissioning
2023
Draft