## OEM vs USSK scope
[23 empty] | AA | [18 empty] | AR | [17 empty] | FAC
NEW ASU PLANT - Air Products
[25 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37
HMG USSK CAPEX | time axis 2023-01-01 to 2027-12-01
AA | bar: 2024-10-01
AR
OEM contract negotiation & signature | bar: 2024-07-01 to 2024-11-01
Engineering documentation
OEM Basic Design | bar: 2024-12-01 to 2025-06-01
OEM Detail Engineering | bar: 2025-07-01 to 2026-02-01
Basic Engineering (EPCM) | bar: 2025-01-01 to 2025-09-01
Detail Engineering (EPCM) | bar: 2025-10-01 to 2026-05-01
Permit Engineering
EIA Documentation / USSK + EPCM | bar: 2025-03-01 to 2025-06-01
Land-use Permit Documentation | bar: 2025-07-01 to 2025-10-01
Building Permit Documentation | bar: 2025-11-01 to 2026-03-01
Permitting process
EIA Permit | bar: 2025-07-01 to 2025-10-01
Land-use Permit | bar: 2025-11-01 to 2026-03-01
Building Permit | bar: 2026-04-01 to 2026-08-01
Construction - Tenders & Contracts
Civil | bar: 2026-04-01 to 2026-07-01
Steel structures | bar: 2026-04-01 to 2026-07-01
Technology | bar: 2026-04-01 to 2026-07-01
Electricity | bar: 2026-04-01 to 2026-07-01
Manufacturing and Deliveries
OEM Manufacturing | bar: 2025-04-01 to 2027-01-01
FOB & FAS Transport | bar: 2025-10-01 to 2027-03-01
Manufacturing
Deliveries
Construction and Start-up
OEM Supervision
Construction works | bar: 2026-08-01 to 2027-07-01
Mechanical works | bar: 2026-11-01 to 2027-08-01
Technology Installation | bar: 2026-11-01 to 2027-10-01
Electricity connection | bar: 2027-01-01 to 2027-10-01
Start up | bar: 2027-11-01
As-build Documentation | bar: 2027-11-01 to 2027-12-01
FAC | bar: 2027-11-01 to 2027-12-01