## Section-3_Scope Matrix
Appendix 1a : OA40 ASU : AP / CLIENT SCOPE SPLIT
Rev. | Sl No. | Tag | Description | Qty | Basic Eng (B) | Detail Eng (D) | Supply (S) | Transportation (Ex Works to Port of Origin) | Transportation (Port of Origin to DAP Site) | Erection (E ) | Remarks
| 1 |  | Issue Monthly status report (AP scope) | - | AP | AP | AP |  | - | - | On AP format.
| 2 |  | Model Review - (AP Scope) |  | AP | AP | AP |  | - | - | 60/90 % review. Participation by Client
| 3 |  | P&ID ( AP Scope) |  | AP | AP | - |  | - | - | Excluding SVD (Storage, Vaporization, Disctribution)
| 4 |  | HAZOP |  | AP | AP | - |  | - | - | AP to conduct HAZOP for entire plant excluding SVD Area. Client will participate. Closure of HAZOP Points pertaining to CLIENT'S Scope of Supply will be by CLIENT. Cost implication arising from Hazop study shall be in Client's account
| 5 |  | Permits |  | Client | Client | Client | - | - | - | Supporting dcuments required for statuatory approval by AP
| 6 |  | Define applicable country codes and standards |  | Client | Client | Client | - | - | -
| 7 |  | Import License, duties & taxes |  | Client | Client | Client | - | - | -
| 8 |  | Performance Test |  | AP | AP | AP |  | - | - | One AP process engineer will be sent to site. Remote support from AP home office if required.
| 9 |  | Transportation study |  | - |  | Client
|  | CP | Compression
| 10 | V102 | MAC Inlet Filter | 1 | AP | AP | AP | AP | Client | Client
| 11 | F203 | MAC Suction duct | 1 | AP | AP | Client | Client | Client | Client
| 12 | V104 | MAC Inlet Silencer (part of filter V102) | 1 | AP | AP | AP | AP | Client | Client
| 13 | K111 | Main Air Compressor | 1 | AP | AP | AP | AP | Client | Client
| 14 | D111 | MAC Motor | 1 | AP | AP | AP | AP | Client | Client
| 15 | V113 | MAC Discharge Vent Silencer | 1 | AP | AP | AP | AP | Client | Client
| 16 | K131 | Booster Air Compressors | 1 | AP | AP | AP | AP | Client | Client
| 17 | D131 | BAC Motor | 1 | AP | AP | AP | AP | Client | Client
| 18 | E136 | BAC After coolers (Part of Compressor Package) | 1 | AP | AP | AP | AP | Client | Client
| 19 | V135 | BAC Discharge silencer | 1 | AP | AP | AP | AP | Client | Client
| 20 | K701 | GAN Compressor -1 | 1 | AP | AP | AP | AP | Client | Client
| 21 | K702 | GAN Compressor -2 | 1 | AP | AP | AP | AP | Client | Client
| 22 | K703 | GAN Compressor -3 | 1 | AP | AP | AP | AP | Client | Client
| 23 | D701 | GAN Compressor Motor - 1 | 1 | AP | AP | AP | AP | Client | Client
| 24 | D702 | GAN Compressor Motor - 2 | 1 | AP | AP | AP | AP | Client | Client
| 25 | D703 | GAN Compressor Motor - 3 | 1 | AP | AP | AP | AP | Client | Client
| 26 | E701 | GAN Compressor After coolers (Part of Compressor Package) | 1 | AP | AP | AP | AP | Client | Client
| 27 |  | Interconnecting Piping to and from compressors | lot | AP | AP | Client | Client | Client | Client
|  | FE | Air Pre-Cooling & Purification System
| 28 | C161 | DCAC Vessel | 1 | AP | AP | AP | AP | Client | Client
| 29 | C171 | Chilled Water Tower | 1 | AP | AP | AP | AP | Client | Client
| 30 | C182A/B | Adsorber Vessels | 2 | AP | AP | AP | AP | Client | Client
| 31 | E182 | Electrical Regeneration Heater with Controller | 1 | AP | AP | AP | AP | Client | Client
| 32 | G161A/B | DCAC Pumps (2 x 100%) | 2 | AP | AP | AP | AP | Client | Client
| 33 | G171A/B | Chilled Water Pumps (2 x 100%) | 2 | AP | AP | AP | AP | Client | Client
| 34 | N161 | DCAC Packing | 1 lot | AP | AP | AP | AP | Client | Client | packings to be installed at site
| 35 | N171 | Chilled Water Tower Packing | 1 lot | AP | AP | AP | AP | Client | Client | packings to be installed at site
| 36 | N181 | Adsorbent - Molecular Sieve | 1 lot | AP | AP | AP | AP | Client | Client
| 37 | N184 | Adsorbent - Alumina | 1 lot | AP | AP | AP | AP | Client | Client
| 38 | V184 | Depressurisation Vent Silencer | 1 | AP | AP | AP | AP | Client | Client
| 39 | V185 | Reactivation Vent Silencer | 1 | AP | AP | AP | AP | Client | Client
| 40 | W1611 | DCAC Internals (incl. water distributors, packing hold-down grids, packing support grids) | 1 lot | AP | AP | AP | AP | Client | Client | Internals to be installed at site
| 41 | W1711 | Chilled water Tower Internals | 1 lot | AP | AP | AP | AP | Client | Client | Internals to be installed at site
| 42 | W1821 | TSA Vessel Internal Screens | 2 lot | AP | AP | AP | AP | Client | Client
| 43 | W1822 | TSA Vessel Internal Filters | 2 | AP | AP | AP | AP | Client | Client
| 44 |  | Interconnecting Piping between equipment |  | AP | AP | Client | Client | Client | Client
|  | CS | Cryogenic System
| 45 | S210/ S470 | S210 (Main - HP/LP Column Box ), S470 (Argon column box) | [7 empty] | Supplied in split boxes based on transport feasability. The boxes shall be joined in Horizontal position & then erected
| 46 | C211 | HP Column | 1 | AP | AP | AP | AP |  |  | Part of Cold Box
| 47 | C212 | LP Column | 1 | AP | AP | AP | AP |  |  | Part of Cold Box
| 48 | E213 | Reboiler | 1 | AP | AP | AP | AP |  |  | Part of Cold Box
| 49 | E221 | LOX Sub cooler | 1 | AP | AP | AP | AP |  |  | Part of Cold Box
| 50 | E222 | LIN Sub cooler | 1 | AP | AP | AP | AP |  |  | Part of Cold Box
| 51 | C401 | Argon Column | 1 | AP | AP | AP | AP |  |  | Part of Cold Box
| 52 | C409 | Argon Column Reboiler Vessel | 1 | AP | AP | AP | AP |  |  | Part of Cold Box
| 53 | E401 | Argon column overhead condenser | 1 | AP | AP | AP | AP |  |  | Part of Cold Box
| 54 | E462 | Pure Argon Column Overhead Condenser | 1 | AP | AP | AP | AP |  |  | Part of Cold Box
| 55 | C461 | Pure Argon Column | 1 | AP | AP | AP | AP |  |  | Part of Cold Box
| 56 | C465 | LIN Phase Separator | 1 | AP | AP | AP | AP |  |  | Part of Cold Box
| 57 | E461 | Pure Argon Column Reboiler Condenser | 1 | AP | AP | AP | AP |  |  | Part of Cold Box
| 58 | E413 | Argon product Condenser | 1 | AP | AP | AP | AP |  |  | Part of Cold Box
| 59 | G402 | Argon Column CLOX Return Pump (2x100%) | 2 | AP | AP | AP | AP | Client | Client
| 60 | J010 | Valves and Instrumentation | 1 lot | AP | AP | AP | AP |  |  | Part of Cold Box
| 61 | L110 | Pipes & Fittings inside Box | 1 lot | AP | AP | AP | AP |  |  | Part of Cold Box
| 62 | L200 | Manual Valves | 1 lot | AP | AP | AP | AP |  |  | Part of Cold Box
| 63 | L210 | Special Piping Items | 1 lot | AP | AP | AP | AP |  |  | Part of Cold Box
| 64 | TJ00 | Piping Transition Joints | 1 lot | AP | AP | AP | AP |  |  | Part of Cold Box
| 65 | S120 | Cold Box Structure | 1 lot | AP | AP | AP | AP | Client | Client
| 66 |  | Painting | 1 lot | AP | AP | AP | AP |  | Client | Touch up paint supply and application at site by Client
| 67 | N003 | Perlite / Rockwool | 1 lot | AP | AP | Client |  | Client | Client | Raw Perlite / Rockwool to be expanded & filled at site.
| 68 |  | Cold box access structures (incl. ladders and platforms) | 1 lot | AP | AP | Client | Client | Client | Client
| 69 |  | Aviation lamp on cold box | 1 lot | AP | AP | Client | Client | Client | Client | if required
|  | CS | S200A/B - MHE Box, (listed equipment is within or part of box envelope)
| 70 | E200 | Main Heat Exchanger | 1 | AP | AP | AP | AP |  |  | Part of S200.
| 71 | J010 | Valves and Instrumentation | 1 lot | AP | AP | AP | AP |  |  | Part of S200.
| 72 | L100 | Pipes & Fittings inside Box | 1 lot | AP | AP | AP | AP |  |  | Part of S200.
| 73 | L200 | Manual Valves | 1 lot | AP | AP | AP | AP |  |  | Part of S200.
| 74 | L210 | Special Piping Items | 1 lot | AP | AP | AP | AP |  |  | Part of S200.
| 75 | L203 | Piping Transition Joints | 1 lot | AP | AP | AP | AP |  |  | Part of S200.
| 76 | S120 | Cold Box Structure | 1 | AP | AP | AP | AP | Client | Client
| 77 |  | Painting | 1 lot | AP | AP | AP |  |  | Client | Touch up paint supply and application at site by Client
| 78 | N003 | Perlite / Rockwool | 1 lot | AP | AP | Client |  | Client | Client | Raw Perlite / Rockwool to be expanded & filled at site.
| 79 |  | Cold box access structures (incl. ladders and platforms) | 1 lot | AP | AP | Client | Client | Client | Client
|  | CS | Compander Box (listed equipment is within or part of box envelope)
| 80 | J010 | Valves and Instrumentation | 1 lot | AP | AP | AP |  | Client | Client | Part of the cross over box
| 81 | L100 | Pipes & Fittings inside Box | 1 lot | AP | AP | AP |  | Client | Client | Part of the cross over box
| 82 | L200 | Manual Valves | 1 lot | AP | AP | AP |  | Client | Client | Part of the cross over box
| 83 | L203 | Piping Transition Joints | 1 lot | AP | AP | AP |  | Client | Client | Part of the cross over box
| 84 |  | Painting | 1 lot | AP | AP | AP |  |  | Client | Touch up paint supply and application at site by Client
| 85 | N003 | Perlite/Rockwool | 1 lot | AP | AP | Client |  | Client | Client | Raw Perlite / Rockwool to be expanded & filled at site.
|  | CS | Cross-overs (listed equipment is within or part of cross-over envelope)
| 86 | J010 | Valves and Instrumentation | 1 lot | AP | AP | AP |  |  | Client | Part of the cross over box
| 87 | L100 | Pipes & Fittings inside Box | 1 lot | AP | AP | AP |  |  | Client | Part of the cross over box
| 88 | L200 | Manual Valves | 1 lot | AP | AP | AP |  |  | Client | Part of the cross over box
| 89 | L203 | Piping Transition Joints | 1 lot | AP | AP | AP |  |  | Client | Part of the cross over box
| 90 |  | Cross-over structure | 1 | AP | AP | AP |  |  | Client | Part of the cross over box
| 91 |  | Painting | 1 lot | AP | AP | AP |  |  | Client | Touch up paint supply and application at site by Client
| 92 | N003 | Perlite/Rockwool | 1 lot | AP | AP | Client |  | Client | Client | Raw Perlite / Rockwool to be expanded & filled at site.
|  | CS | Cold Box Yard
| 93 | K262 | Compander with lube oil system | 1 | AP | AP | AP | AP | Client | Client
| 94 | E262 | Compander after cooler | 1 | AP | AP | AP | AP | Client | Client
| 95 | E871 | Disposal Vaporiser |  | AP | AP | AP | AP | Client | Client
| 96 | G231 | LOX Process Pumps (2x100%) | 2 | AP | AP | AP | AP | Client | Client
| 97 | S230/S231 | LOX Pump Box and Valve Box | 1 | AP | AP | AP | AP | Client | Client
| 98 | J010 | Valves and Instrumentation | 1 lot | AP | AP | AP | AP | Client | Client | Upto tie-in point between AP and Client
| 99 | L200 | Manual Valves | 1 lot | AP | AP | AP | AP | Client | Client | Upto tie-in point between AP and Client
| 100 | L100 | Interconnecting Piping between equipment |  | AP | AP | Client | Client | Client | Client
| 101 | L009 | Pipe Supports | 1 lot | AP | AP | Client | Client | Client | Client
| 102 | L135 | Liquid Pipe lines and supports | 1 lot | AP | AP | Client | Client | Client | Client
| 103 | N003 | Pipe Insulation Materials | 1 lot | AP | Client | Client | Client | Client | Client
| 104 | S001 | Platforms & Ladders (if required) | 1 lot | AP | Client | Client | Client | Client | Client
| 105 | S003 | Pipe racks | 1 lot | AP | AP | Client | Client | Client | Client | AP typical connection details shall be provided for reference. Connection design by EPC fabricator. Erection and fabrication drawings by EPC fabricator.
| 106 |  | Support structures for E&I cable tray, pipes, valves, instruments etc within Cold Box Area |  | Client | Client | Client | Client | Client | Client
|  | SV | Storage , Vaporisation & Distribution
| 107 | SV | Equipment
| 108 | T473 | LAR Storage Tank |  | Client | Client | Client | Client | Client | Client
| 109 | T621 | LOX Storage Tank |  | Client | Client | Client | Client | Client | Client
| 110 | T721 | LIN Storage Tank |  | Client | Client | Client | Client | Client | Client
| 111 | T732 | Seal Gas Tank 30 KL(with pressure and level indication in DCS) |  | Client | Client | Client | Client | Client | Client
| 112 | E477 | LAR Storage Tank PBU |  | Client | Client | Client | Client | Client | Client
| 113 | E628 | LOX Storage Tank PBU |  | Client | Client | Client | Client | Client | Client
| 114 | E728 | LIN Storage Tank PBU |  | Client | Client | Client | Client | Client | Client
| 115 | E739 | MP LIN ( Seal Gas / Instrument air) Storage tank PBU |  | Client | Client | Client | Client | Client | Client
| 116 | E641 | HP LOX Backup Vaporiser |  | Client | Client | Client | Client | Client | Client
| 117 | E645 | MP LOX Backup Vaporiser |  | Client | Client | Client | Client | Client | Client
| 118 | E741 | LIN Backup Vaporiser |  | Client | Client | Client | Client | Client | Client
| 119 | E801 | LAR Backup Vaporiser |  | Client | Client | Client | Client | Client | Client
| 120 | E744 | LIN Ambinet Vaporiser for seal gas |  | Client | Client | Client | Client | Client | Client
|  | SV | Pump Boxes
| 121 | G641A/B | LOX Back up Pumps |  | Client | Client | Client | Client | Client | Client
| 122 | G741A/B | LIN Backup Pumps |  | Client | Client | Client | Client | Client | Client
| 123 | G801A/B | LAR Backup Pumps |  | Client | Client | Client | Client | Client | Client
| 124 | S641 A/B | LOX Process and Back up Pump Box and Valve Box |  | Client | Client | Client | Client | Client | Client
| 125 |  | Piping from Tank to Backup Vaporizer |  | Client | Client | Client | Client | Client | Client
| 126 |  | Piping from Cold Box to Tank |  | Client | Client | Client | Client | Client | Client
| 127 |  | Piping from Backup Vaporizer to ASU Battery Limit |  | Client | Client | Client | Client | Client | Client
| 128 |  | Support structures for E&I cable tray, pipes, valves, instruments etc within SVD area |  | Client | Client | Client | Client | Client | Client
| 129 |  | Impulse tubing, fittings, for SVD instrumentation |  | Client | Client | Client | Client | Client | Client
| 130 |  | Instrument Air Line including valves, instruments, cabling and impulse tubing |  | Client | Client | Client | Client | Client | Client
| 131 |  | Junction boxes, branch cabling including trays from field instruments upto Junction Box for SVD |  | Client | Client | Client | Client | Client | Client
| 132 | N003 | Perlite/Rockwool | 1 lot | Client | Client | Client | Client | Client | Client
|  | PW | Plant wide
| 133 | PW | Electrical - 6.6 kV down stream | [7 empty] | 6,3 kV connection from T80
| 134 | P220 | 6.6 kV MV Switchgear 4000A | 1 | AP | AP | AP | AP | Client | Client
| 135 | P221 | 6.6 kV MV Switchgear 1250A (ICOG panel) | 1 | AP | AP | AP | AP | Client | Client
| 136 | P222 | 6.6 kV MV Switchgear 1250A (ICOG panel) | 1 | AP | AP | AP | AP | Client | Client
| 137 | P410 | 400V LV Switchgear excluding VFD and Soft Starter, 2000A | 1 | AP | AP | AP | AP | Client | Client
| 138 | P470 | 690V Thyristorised Control Panel, 2500A | 1 | AP | AP | AP | AP | Client | Client | 400V standard in EU
| 139 | P310 | MF VFD / LCI for starting of Compressor motors |  | AP | Client | Client | Client | Client | Client | As Basic Eng, AP will provide all motor inputs required for sizing by Client/ client's vendor
| 140 |  | 6.3/0.415 kV Distribution Transformer for LV loads |  | Client | Client | Client | Client | Client | Client | Electrical load summary input by AP - 400V standard in EU
| 141 |  | 6.3/0.790 kV Distribution Transformer for heater loads |  | Client | Client | Client | Client | Client | Client | Electrical load summary input by AP - 400V standard in EU
| 142 | P530 | Lighting Transformer |  | Client | Client | Client | Client | Client | Client
| 143 |  | MV / LV Capacitors for power factor improvements |  | Client | Client | Client | Client | Client | Client | if required by client
| 144 |  | All MV/LV, Power and Control Cables, Glands and Termination kits |  | Client | Client | Client | Client | Client | Client
| 145 |  | MV/LV Bus Ducts |  | Client | Client | Client | Client | Client | Client
| 146 |  | LV VFD / Soft Starters |  | Client | Client | Client | Client | Client | Client
| 147 |  | UPS |  | Client | Client | Client | Client | Client | Client
| 148 |  | Battery Chargers |  | Client | Client | Client | Client | Client | Client
| 149 |  | Lighting / Small Power Distribution Boards |  | Client | Client | Client | Client | Client | Client
| 150 |  | Lighting fixtures |  | Client | Client | Client | Client | Client | Client
| 151 |  | Juction Boxes |  | Client | Client | Client | Client | Client | Client
| 152 |  | Cable Trays and Supports |  | Client | Client | Client | Client | Client | Client
| 153 |  | Earthing and Lightning Protection |  | Client | Client | Client | Client | Client | Client
| 154 |  | Electrical Heat Tracing |  | Client | Client | Client | Client | Client | Client | Lines requiring heat tracing will be indicated in P&IDs
| 155 |  | Emergency DG |  | Client | Client | Client | Client | Client | Client
| 156 |  | SCADA |  | Client | Client | Client | Client | Client | Client
| 157 |  | Electrical Installation materials |  | Client | Client | Client | Client | Client | Client
| 158 |  | HVAC |  | Client | Client | Client | Client | Client | Client | Heat load for AP supplied equipment shall be provided.
| 159 |  | Aviation lamp on cold box |  | Client | Client | Client | Client | Client | Client | if required by local regulations
| 160 |  | Cathodic protection |  | Client | Client | Client | Client | Client | Client | if required.
|  | PW | Piping
| 161 |  | Interconnecting piping,Pipe supports & fittings between the equipment | 1 lot | AP | AP | Client | Client | Client | Client
| 162 |  | Manual valves (Cryo & Warm) |  | AP | AP | AP | AP | Client | Client | Within AP Battery limit
| 163 |  | Special Piping Items (Cryo & Warm) |  | AP | AP | AP | AP | Client | Client | Within AP Battery limit
| 164 |  | Flanges, Gaskets | 1 lot | AP | AP | Client | Client | Client | Client
| 165 |  | Utility piping with in B/L | 1 lot | AP | AP | Client | Client | Client | Client
| 166 |  | Underground Piping work for Cooling Water line | 1 lot | Client | Client | Client | Client | Client | Client | if required.
| 167 |  | Underground Piping for Sanitary, OWS, Storm water & RCC Cover of Storm water Drains, Waste Water (blowdown) and soak pits | 1 lot | Client | Client | Client | Client | Client | Client | if required.
|  | PW | Control & Instrumentation | [7 empty] | for ASU plant
| 168 | J030 | DCS | 1 | AP | AP | AP | AP | Client | Client
| 169 |  | Fiber Optic Cable from Control room to AP Battery limit |  | Client | Client | Client | Client | Client | Client
| 170 | J050 | Analysers |  | AP | AP | AP | AP | Client | Client
| 171 | J051 | Calibration Gases | 1 lot | AP | Client | Client | Client | Client | Client | Supply till successful commissioning - Please explain
| 172 | J053 | Analyser panel | 1 | AP | AP | AP | AP | Client | Client
| 173 | J040 | Field instruments | 1 lot | AP | AP | AP | AP | Client | Client | Within AP Battery Limit
| 174 | J010 | Control Valves | 1 lot | AP | AP | AP | AP | Client | Client | Within AP Battery Limit
| 175 | J020 | Relief valves | 1 lot | AP | AP | AP | AP | Client | Client | Within AP Battery Limit
| 176 | J090 | Instrument Tubes | 1 lot | Client | Client | Client | Client | Client | Client
| 177 | J090 | Instrument cables | 1 lot | Client | Client | Client | Client | Client | Client
| 178 |  | Sample handling system | 1 | AP | Client | Client | Client | Client | Client
| 179 | J090 | Tubing, JBs & Hook-up | 1 lot | Client | Client | Client | Client | Client | Client
| 180 | J040 | Room Analysers (control/analyser/Warehouse/Stores/any other rooms/buildings is in CLIENT scope. |  | Client | Client | Client | Client | Client | Client
| 181 |  | Canopy for all instruments |  | Client | Client | Client | Client | Client | Client
| 182 | CW | Cooling Water System |  | Client | Client | Client | Client | Client | Client
|  | PW | Miscellaneous
| 183 |  | Air analysis |  | Client | Client | Client | Client | Client | Client
| 184 |  | Plant Operating tools/tackles | 1 lot | Client | Client | Client | Client | Client | Client
| 185 |  | Fire Alarm System, Hydrants |  | Client | Client | Client | Client | Client | Client
| 186 |  | Telecommunications |  | Client | Client | Client | Client | Client | Client
| 187 |  | PA system | 1 lot | Client | Client | Client | Client | Client | Client
| 188 |  | All Permits & approvals |  | Client | Client | Client | Client | Client | Client
| 189 |  | Plot for the proposed plant |  | Client | Client | Client | Client | Client | Client
| 190 |  | Other Supplies
| 191 | N500 | Initial fill for machines (Lubrication oil) | 1 lot | AP | Client | Client | Client | Client | Client | First Fill till commissioning including Flushing Oil (excluding tanker filling pumps) till commissioing
|  | PW | Spares
| 192 |  | Commissioning Spares - AP supplied eqpt. | 1 lot | AP | AP | AP | AP | Client | Client | commissioning spares typically are limited to bonnet gaskets and fasteners.
| 193 |  | Capital Spares (for AP supplied equipment) | 1 lot | AP | AP | AP | AP | Client | Client | 1 no. Rotors for Compressors (MAC, BAC, GAN), 1 no. Plug in for Compander only
| 194 |  | 2 Year Operating Spares (for AP supplied Equipments) | 1 lot | AP | AP | Option | Option | Client | Client | AP shall provide list with Technical Proposal.
|  | PW | Civil & Structural
| 195 |  | Civil Work - foundation |  | Client | Client | Client | Client | Client | Client | AP shall provide equipment loads for supplied equipment.
| 196 |  | All civil works incl soil analysis, site clearing, leveling,piling, buildings, equipment foundations ,earthing pits, roads & pavement |  | Client | Client | Client | Client | Client | Client
| 197 |  | Geotechnical and topographical survey report |  | Client | Client | Client |  | - | -
| 198 |  | Pavement ,walkway & Gravelling |  | Client | Client | Client | Client | Client | Client
| 199 |  | Safety signs |  | Client | Client | Client | Client | Client | Client
| 200 |  | ASU Plot Boundary wall |  | Client | Client | Client | Client | Client | Client | if required.
| 201 |  | EOT Crane - in Compressor house | 1 | Client | Client | Client | Client | Client | Client | AP will advise the EOT capacity only during detailed engineering as part of Basic Engineering
| 202 |  | All Monorails, Hoists and Chain Pulley Wherever applicable. | 1 lot | Client | Client | Client | Client | Client | Client | As required.
| 203 |  | Firewall(s) | 1 lot | Client | Client | Client | Client | Client | Client | if required.
| 204 |  | Buildings as per list below :
| 205 |  | Compressor Shed | 1 | Client | Client | Client | Client | Client | Client | AP shall provide compressor shed sizing as part of basic engineering, further detailing by client.
| 206 |  | Electrical room / PDC | 1 | CLient | Client | Client | Client | Client | Client
| 207 |  | Control Room | 1 | Client | Client | Client | Client | Client | Client | AP shall provide control room size as part of basic engineering, further detailing by client.
| 208 |  | Admin Block | 1 | Client | Client | Client | Client | Client | Client
| 209 |  | Stores, Workshop | 1 | Client | Client | Client | Client | Client | Client
| 210 |  | Analyser room | 1 | Client | Client | Client | Client | Client | Client | AP shall provide the size required for Analyser room.
| 211 |  | Interior works for buildings including workstations, furniture etc. |  | Client | Client | Client | Client | Client | Client
| 212 |  | Drainage water line (storm, contaminated & waste water) |  | Client | Client | Client | Client | Client | Client | Client to connect the existing network at ASU B/L.
| 213 |  | Access platforms & ladders for equipment (if required by Client) |  | AP | Client | Client | Client | Client | Client
| 214 |  | Anchor bolts / Template |  | AP | Client | Client | Client | Client | Client
| 215 |  | Foundation Bolts (embedded) |  | AP | Client | Client | Client | Client | Client
| 216 |  | Grouting (Cementetious / Epoxy) |  | AP | Client | Client | Client | Client | Client
| 217 |  | Utilities Facilities |  | Client | Client | Client | Client | Client | Client
| 218 |  | Horizontal Joining of Coldboxes at site |  | AP | AP | AP |  | - | - | Client to provide suitable laydown area for joining coldboxes and Aluminium piping, required lighting & weather protection, Electricity, Weld gases, cranes, NDE services, Erected Scaffolding for joining and inspection, pressure test medium. During site joinging of Coldboxes the column and Aluminium piping shall be welded by AP personnel, the Coldbox carbon steel /structure welding shall be done by installation contractor at site under AP supervision.
General Notes:
|  | 1 | The ASU plant is considered as SAFE & Non Hazardous
Pre Erection podklady pre vystavbu, Commissioning plan, manualy na obsluhu a udrzbu

## Doc Content (hidden)
Disclipline | Deliverable | Duty Spec | 1st Issue | Typicals | Final
General |  | "4-lines" spec, with information on overall duty, materials of construction, etc | varies by deliverable, but generally includes major items of detail, or generic information. but not all details or project specific details. May allow further design or manufacture to commence. | Provides detail information, but not project specific tags or quantities | Full detail to allow manufacture or construction to be completed. Includes resonsiblity for as-builts
Process
| H&MB - P1 Review |  |  |  | Refer to work instruction APP-xxxxx Design Review
Electrical - Engineering
| HV, LV Single Line diagram | n/a | Major equipment configuration, generalised loads only
Electrical - Equipment
| HV Transformer Spec | Rating, impedance, cooling type, configuration
Process Controls & Instruments
Instrument Summary
| DCS - Control System |  | Hardware requirements, and system general arrangement |  | As 1st Issue + I/O quantities
| Analyser Panel |  | Analyser summary, panel outline general arrangement, typical tubing & electrical scematics (one per type of analysers) |  | Full detail to enable panel build & test